## Failover
| 7:45 | 8:00 | DR Test Bridge Opens for Readiness Check | MS Teams Link: https://teams.microsoft.com/l/team/19%3aW29NXuc1wdrnyNvpxPPHvSC5DkEKoaoe42NSCb-A1os1%40thread.tacv2/conversations?groupId=e81fbd53-df92-43dc-859b-2906b38e2c01&tenantId=7bc8ad67-ee7f-43cb-8a42-1ada7dcc636e
Date | Start time | End time | Activity | Outcome | Team responsible | Achieved Start Time | Achieved Completion Time | Success Y/N | Evidence collected
| 8:00 | 8:05 | Confirm Backup completion | DR test can commence | Wintel | 8:00 | 8:05
| 8:10 | TBC | Active Directory production server taken down | All DC network traffic forced to DR link | Wintel | 8:00 | 8:05 |  |  | SYDPINFDCG01.corp.ad.tullib.com [DS] Site: Sydney SYDPINFDCG02.corp.ad.tullib.com [DS] Site: Sydney
| 8:15 | 8:20 | Login test across all domains | Checks if AD failover is successful | Wintel | 8:18 | 8:30
|  |  | Exchange available on-prem |  | Wintel | 9:30 | 9:49 |  |  | Singapore
| 9:20 | 9:40 | DNS change to be completed for GBOSAPCL(Database Name) |  | Wintel | 9:04 | 9:23 |  |  | change dns names
| 12:00 | 12:15 | Update the alias cName |  | Wintel | 10:15 | 10:19
| 9:40 | 10:00 | DNS change to be completed on TMS DR servers and Flush | Dependent of Database DNS change replicating on database being on-line | Wintel | 9:04 | 9:23
| 9:30 | 9:50 | Changes DNS to DR servers for ETC/GTN - AGB and Flush |  | Wintel | 9:04 | 9:23

## Prod
Start time | End time | Activity | Team responsible | Dependency | Outcome | Achieved Start Time | Achieved Completion Time | Success Y/N | Evidence collected
(Singapore Time)
13:05 |  | Failback application services back to Castlereagh Exchange (On-Prem Only) to be completed once all DR applications have been taken down successfully | Wintel
13:30 | 13:45 | Login test across all domains | Wintel |  | Checks if AD failed back is successful
13:25 | 13:30 | Active Directory production server promoted | Wintel | AD failover success or has been failedback | All DC network traffic forced to Primary link
|  | Exchange available in 0365 validate connectivity | Wintel |  |  | 17:40 | 17:41 | Y
14:40 | 15:00 | DNS change to be completed for GBOSAPCL back to Primary | Wintel |  |  |  |  | Y
15:25 | 15:35 | Update the alias cName | Wintel |  |  |  |  | Y
15:00 | 15:10 | Changes DNS to Primary servers for ETC/GTN - AGB | Wintel |  |  | 15:07 | 15:22 | Y
16:05 | 16:10 | Reactivate Alerting for Infrastructure and Applications | All support teams involved

## Sheet1
Date | Start time | End time | Activity | Outcome | Team responsible
(Singapore Time)
Friday 05/19/2023 | 15:00 | 15:15 | Go No go meeting | Approval to go ahead | All
|  |  | Ensure all applications are in-sync with correct versions on Production & DR | Approval to go ahead | All
| 15:45 | 16:00 | Final comms in preparation for test | All stakeholders aware of decision | All
| 8:00 | 8:05 | Surpress Alerting for Infrastructure and Applications |  | Individual teams
| 8:00 | 8:05 | Confirm Backup completion | DR test can commence | Wintel
| 8:10 | TBC | Active Directory production server taken down | All DC network traffic forced to DR link | Wintel
| 8:15 | 8:20 | Login test across all domains | Checks if AD failover is successful | Wintel
|  |  | Exchange available on-prem |  | Wintel
| 9:20 | 9:40 | DNS change to be completed for GBOSAPCL(Database Name) |  | Wintel
| 12:00 | 12:15 | Update the alias cName |  | Wintel
| 9:40 | 10:00 | DNS change to be completed on TMS DR servers and Flush | Dependent of Database DNS change replicating on database being on-line | Wintel
| 9:30 | 9:50 | Changes DNS to DR servers for ETC/GTN - AGB and Flush |  | Wintel