## Scope
Application | Instance | Business Unit | Technical Owner | Support Owner | Support Team | Primary contact | Additional Support teams required to perform DR failover | DR plan available | RTO/RPO reviewed | Downstream impact actions required to revert DR test ahead of Monday? | Action list
NFA | NFA - AM Prod | CORPORATE | Tatyana.Vasilevsky@tpicap.com | Declan.Wyatt@tpicap.com | IAS | Edrick/Declan | Wintel, DBA | Yes | Yes | After DR Test, connections to CACHE_GCD on NFA DB servers from various systems need to be checked - Jig
SHARC | Front Office - AM Prod | GLOBAL BROKING | Tony.Castellano@tpicap.com | Declan.Wyatt@tpicap.com | IAS/DBA | Jig/Wong | Wintel | Yes | Yes
Active Directory | Active Directory - GLOBAL - AM Prod Active Directory - ICAPROOT - AM Prod Active Directory - US - AM Prod | ISM | Chris.Stradling@tpicap.com | Harjot.Kandola@tpicap.com | Wintel | Harjot | None | Yes | Yes
tpEnergyTrade | tpEnergyTrade - AM Prod | ENERGY&COMMODITIES | Mark.Norton@tpicap.com | Declan.Wyatt@tpicap.com | IAS | Edrick/Declan | Wintel, DBA | Yes | Yes

## Runbook
Date | Activity | Detail
DR Test Starts |  |  | RTO
Sat 12/10/22 | DR Test Teams Channel Opens for Readiness Check | All participants dial in to confirm readiness to begin
| Take down application services in Primary - NFA, tpEnergyTrade, Sharc, Active Directory | Applications will be gracefully shutdown after any batch processing has completed & take screenshot evidence of services down in Primary | Note down the start time ot measure RTO - A
| Bring up SQL DBs for NFA and tpEnergyTrade in DR using Double Take Failover | Take screenshot evidence database down in Primary and Up in DR | Note down the time it took to failover database
| DNS changes for Failover | Take screenshot evidence of DNS changes | Note down the time it took to do DNS changes
| Failover NFA | Take screenshot evidence application down in Primary and Up in DR | Note down the end time to measure RTO - B RTO is B-A
| Failover tpEnergyTrade | Take screenshot evidence application down in Primary and Up in DR | Note down the end time to measure RTO - B RTO is B-A
| Failover Sharc Database | Take screenshot evidence database down in Primary and Up in DR | Note down the end time to measure RTO - B RTO is B-A
| Failover ActiveDirectory | Take screenshot evidence application down in Primary and Up in DR | Note down the end time to measure RTO - B RTO is B-A
| Test NFA | Take screenshot evidence of testing in DR
| Test tpEnergyTrade | Take screenshot evidence of testing in DR
| Test Sharc | Take screenshot evidence of testing in DR
| Test Active Directory | Take screenshot evidence of testing in DR
Take down application services in DR - NFA, tpEnergyTrade
Bring up SQL DBs for NFA and tpEnergyTrade in Primary using Double Take Failover
DNS Changes for Failback
Failback NFA
Failback tpEnergyTrade
Failback Sharc Database
Failback ActiveDirectory
Test NFA
[!OC([1033])!] | Test tpEnergyTrade
......................................................................................................................................... | Test Sharc
Test Active Directory
Test Completed