## Server Setup Checklist
[5 empty] | Office Addr | For func | serverName | Model | IP address | IP address for iDRAC (Mgt Port) | SN
Servers | 4 servers in Shanghai and 4 servers in Beijing |  |  |  | Shanghai | TC | SHGMBSAPP01 | DELL PowerEdge R750xs | 170.198.160.60 |  | DZ7FZT3
[7 empty] | SHGMBSDB01 | DELL PowerEdge R750xs | 170.198.160.62 |  | CZ7FZT3
Parties Responsible: | Shanghai IT |  |  |  |  | Inv | SHGMBSAPP02 | DELL PowerEdge R750xs | 170.198.160.61 |  | BZ7FZT3
| Global DBA | [5 empty] | SHGMBSDB02 | DELL PowerEdge R750xs | 170.198.160.63 |  | 9Z7FZT3
| Asia MBS2 Support |  |  |  | Beijing | TC | BJGMBSAPP01 | DELL PowerEdge R750xs
| Wintel | [5 empty] | BJGMBSDB01 | DELL PowerEdge R750xs
Go Live | March 2023 |  |  |  |  | Inv | BJGMBSAPP02 | DELL PowerEdge R750xs
[7 empty] | BJGMBSDB02 | DELL PowerEdge R750xs
Schedule | No. | TASK |  | Assign to | Task Dependencies | Comments | Status
Jan 3 - Jan 13 | 1 | Install Windows Server 2019 Standard 64-bit for all the eight servers In Shanghai office - 2 Trade Capture Servers + 2 Invoice Servers; |  | Qingyan |  |  | completed
TBC |  | In Beijing (DR) office - 2 Trade Capture Servers + 2 Invoice Servers |  | Qingyan |  |  | Guochang's team going to complete by this Friday
| 2 | Confirm Shanghai has the Microsoft SQL Server 2019 Enterprise Edition 64-bit licence |  | Qingyan |  |  | No-limit license
| 3 | Set up these drives on the Invoice servers C:\System 500 GB D:\Data 100 GB E:\SQL Data 2 TB F:\SQL Logs 750 GB G:\TempDB 200 GB H:\Backup and Archive 4TB |  | Qingyan | 1,2 |  | Guochang's team going to complete by this Friday
| 4 | Set up these drives on the Trade Capture servers C:\System 500 GB D:\Data 100 GB E:\SQL Data 750 GB F:\SQL Logs 500 GB G:\TempDB 200 GB H:\Backup and Archive 4TB |  | Qingyan | 1,2 |  | Guochang's team going to complete by this Friday
| 5 | Set up NAS Storage |  | Qingyan |  |  | Guochang's team will set up
| 6 | Set up the servers on Cluster |  | Harjot | 3,4
| 7 | Set up access group and rights in Servers |  | Harjot
| 8 | Set up admin access for DBA corp\global sql dba, mbs live user |  | Kelvin | 7
| 9 | Install Microsoft SQL Server 2019 Enterprise Edition 64-bit in all the servers |  | Wong | 2,8
| 10 | Set up access group and rights in Database |  | Wong
| 11 | Allocate Memory Size (SQL - 80%, OS - 20%) on the Invoice servers Allocate Memory Size (SQL - 80%, OS - 20%) on the Trade Capture servers |  | Wong | 9
| 12 | Set up two Invoice Prod [2 node Always On Cluster] Set up two Trade Capture Prod [2 node Always On Cluster] |  | Wong
| 13 | Set up SSRS in Production servers |  | Wong
| 14 | Set up DB replication in Production servers |  | Wong
| 15 | Trade Capture Production Installation |  | MBS2 Team | 13
- Create Trade Capture installation path
- Copy access.xml from azman
- Copy MBS2 latest Trade Capture version
- Set up services - Trade Capture, DCS, Confirmation Adaptor/Manager/Gateway
| 16 | Use existing SHGMBS03 and SHGMBS04 as the application server. Point the connection to the new database servers. |  | MBS2 Team
| 17 | System Testing for Trade Capture Production/STP from DCS to MBS2 |  | Sumscope/MBS2 Team/Wong
| 18 | Invoice Production Installation |  | MBS2 Team
| 19 | System Testing for Invoice Production |  | Wong/MBS2 Team
DCS Connection Details
| DcsWebServiceUrl |  | http://10.249.32.172:8080/ss_tos/ws/modifystatus.mvc
| DcsTradeDetailUrl |  | http://10.249.32.172:8080/ss_tos/jsp/tp/viewDetailfromHyperLinkIrs.jsp?dcsId=
| DcsCustomerServiceUrl |  | http://10.249.32.172:8080/ss_tos/ws/modifycust.mvc
| DcsMbs2ServiceProduction |  | 10.249.32.62:9000

## Shanghai
Datacenter | Shanghai
Kt List
| Rack | Source Device name | Model | S/N | Interface | Source Connector | Type | Destination Connector | Interface | S/N | Model | Destination Device Name | Rack | IP | subnet | Default Gateway | Idrac Account | Idrac Password
| PROD Trade Capture APP | SHGMBSAPP01 | DELL PowerEdge R750xs | DZ7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi3/0/39 | FCW2135C16W | WS-C3850-12X48U-E | SHGNWRK06-3 | 3F-05-16U | 170.198.160.60 | 255.255.255.128 | 170.198.160.1
|  | SHGMBSAPP01 | DELL PowerEdge R750xs | DZ7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi3/0/40 | FCW2135C039 | WS-C3850-12X48U-E | SHGNWRK08-3 | 3F-15-8U | 170.198.160.60 | 255.255.255.128 | 170.198.160.1
|  | iSHGMBSAPP01 | DELL PowerEdge R750xs | DZ7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi1/0/45 | FCW2135D1B4 | WS-C3850-12X48U-E | SHGNWRK06-1 | 3F-06-16U | 10.251.128.30 | 255.255.255.0 | 10.251.128.1 | root | HPFXRAKNFWF9
| PROD Trade Capture DB | SHGMBSDB01 | DELL PowerEdge R750xs | CZ7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi3/0/42 | FCW2135C16W | WS-C3850-12X48U-E | SHGNWRK06-3 | 3F-05-16U | 170.198.160.62 | 255.255.255.128 | 170.198.160.1
|  | SHGMBSDB01 | DELL PowerEdge R750xs | CZ7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi3/0/38 | FCW2135C039 | WS-C3850-12X48U-E | SHGNWRK08-3 | 3F-15-8U | 170.198.160.62 | 255.255.255.128 | 170.198.160.1
|  | iSHGMBSDB01 | DELL PowerEdge R750xs | CZ7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi1/0/7 | FCW2135D1B4 | WS-C3850-12X48U-E | SHGNWRK06-1 | 3F-06-14U | 10.251.129.30 | 255.255.255.0 | 10.251.129.1 | root | W4RE4YMNVAEE
| PROD Invoice APP | SHGMBSAPP02 | DELL PowerEdge R750xs | BZ7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi3/0/40 | FCW2135C16W | WS-C3850-12X48U-E | SHGNWRK06-3 | 3F-05-16U | 170.198.160.61 | 255.255.255.128 | 170.198.160.1
|  | SHGMBSAPP02 | DELL PowerEdge R750xs | BZ7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi3/0/39 | FCW2135C039 | WS-C3850-12X48U-E | SHGNWRK08-3 | 3F-15-8U | 170.198.160.61 | 255.255.255.128 | 170.198.160.1
|  | iSHGMBSAPP02 | DELL PowerEdge R750xs | BZ7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi1/0/46 | FCW2135D1B4 | WS-C3850-12X48U-E | SHGNWRK06-1 | 3F-06-16U | 10.251.128.29 | 255.255.255.0 | 10.251.128.1 | root | E3E9FWY4R9VR
| PROD Invoice DB | SHGMBSDB02 | DELL PowerEdge R750xs | 9Z7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi3/0/41 | FCW2135C16W | WS-C3850-12X48U-E | SHGNWRK06-3 | 3F-05-16U | 170.198.160.63 | 255.255.255.128 | 170.198.160.1
|  | SHGMBSDB02 | DELL PowerEdge R750xs | 9Z7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi3/0/41 | FCW2135C039 | WS-C3850-12X48U-E | SHGNWRK08-3 | 3F-15-8U | 170.198.160.63 | 255.255.255.128 | 170.198.160.1
|  | iSHGMBSDB02 | DELL PowerEdge R750xs | 9Z7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi1/0/8 | FCW2135D1B4 | WS-C3850-12X48U-E | SHGNWRK06-1 | 3F-06-14U | 10.251.129.31 | 255.255.255.0 | 10.251.129.1 | root | FHMRFXNNF39P
Non-PROD T

## Beijing
Datacenter | Beijing
| Rack | Source Device name | Model | S/N | Interface | Source Connector | Type | Destination Connector | Interface | S/N | Model | Destination Device Name | Rack | IP | subnet | Default Gateway | iDrac | Psw
| DR Trade Capture APP | BJGMBSAPP01 | DELL PowerEdge R750xs | JZ7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi1/0/17 | FCW2320L0EV | C9300-48P-A V02 | CNBJGZSS-BDN-COR-01 | C-16-17U | 10.249.32.66 | 255.255.255.0 | 10.249.32.1
|  | BJGMBSAPP01 | DELL PowerEdge R750xs | JZ7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi2/0/17 | FCW2320L0F9 | C9300-48P-A V02 | CNBJGZSS-BDN-COR-02 | C-16-17U | 10.249.32.66 | 255.255.255.0 | 10.249.32.1
|  | iBJGMBSAPP01 | DELL PowerEdge R750xs | JZ7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi1/0/20 | FCW2320L0EV | C9300-48P-A V02 | CNBJGZSS-BDN-COR-01 | C-16-17U | 10.249.32.70 | 255.255.255.0 | 10.249.32.1 | root | PMRRF9443R4A
| DR Trade Capture DB | BJGMBSDB01 | DELL PowerEdge R750xs | HZ7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi1/0/18 | FCW2320L0EV | C9300-48P-A V02 | CNBJGZSS-BDN-COR-01 | C-13-14U | 10.249.32.68 | 255.255.255.0 | 10.249.32.1
|  | BJGMBSDB01 | DELL PowerEdge R750xs | HZ7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi2/0/18 | FCW2320L0F9 | C9300-48P-A V02 | CNBJGZSS-BDN-COR-02 | C-13-14U | 10.249.32.68 | 255.255.255.0 | 10.249.32.1
|  | iBJGMBSDB01 | DELL PowerEdge R750xs | HZ7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi2/0/20 | FCW2320L0F9 | C9300-48P-A V02 | CNBJGZSS-BDN-COR-02 | C-13-14U | 10.249.32.71 | 255.255.255.0 | 10.249.32.1 | root | MXPHRYV3A93A
| DR Invoice APP | BJGMBSAPP02 | DELL PowerEdge R750xs | FZ7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi1/0/15 | FCW2320L0EV | C9300-48P-A V02 | CNBJGZSS-BDN-COR-01 | A-16-17U | 10.249.32.67 | 255.255.255.0 | 10.249.32.1
|  | BJGMBSAPP02 | DELL PowerEdge R750xs | FZ7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi2/0/15 | FCW2320L0F9 | C9300-48P-A V02 | CNBJGZSS-BDN-COR-02 | A-16-17U | 10.249.32.67 | 255.255.255.0 | 10.249.32.1
|  | iBJGMBSAPP02 | DELL PowerEdge R750xs | FZ7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi1/0/14 | FCW2320L0EV | C9300-48P-A V02 | CNBJGZSS-BDN-COR-01 | A-16-17U | 10.249.32.72 | 255.255.255.0 | 10.249.32.1 | root | KN3KAVHFYHV3
| DR Invoice DB | BJGMBSDB02 | DELL PowerEdge R750xs | GZ7FZT3 | NIC1 | RJ45 |  | RJ45 | Gi1/0/16 | FCW2320L0EV | C9300-48P-A V02 | CNBJGZSS-BDN-COR-01 | A-13-14U | 10.249.32.69 | 255.255.255.0 | 10.249.32.1
|  | BJGMBSDB02 | DELL PowerEdge R750xs | GZ7FZT3 | NIC2 | RJ45 |  | RJ45 | Gi2/0/16 | FCW2320L0F9 | C9300-48P-A V02 | CNBJGZSS-BDN-COR-02 | A-13-14U | 10.249.32.69 | 255.255.255.0 | 10.249.32.1
|  | iBJGMBSDB02 | DELL PowerEdge R750xs | GZ7FZT3 | IDRAC | RJ45 |  | RJ45 | Gi2/0/14 | FCW2320L0F9 | C9300-48P-A V02 | CNBJGZSS-BDN-COR-02 | A-13-14U | 10.249.32.73 | 255.255.255.0 | 10.249.32.1 | root | M9YXHP4MV9EW